## Activities
Activity_ID | Activity_Name | Start_Date | End_Date | Duration_Days | Planned_Cost | Actual_Cost | Planned_%_Complete | Actual_%_Complete | Status | Phase
1.1 | Mobilization & Site Office Setup | 2025-04-01 | 2025-04-10 | 10 | 2500000 | 2400000 | 100 | 100 | Completed | Preparation
1.2 | Survey & Setting Out | 2025-04-11 | 2025-04-20 | 10 | 1500000 | 1480000 | 100 | 100 | Completed | Preparation
2.1 | Pile Foundation - Boring | 2025-04-21 | 2025-05-15 | 25 | 12000000 | 11800000 | 100 | 100 | Completed | Foundation
2.2 | Pile Foundation - Concreting | 2025-05-16 | 2025-06-05 | 21 | 9500000 | 9200000 | 100 | 95 | In Progress | Foundation
3.1 | Pier Construction | 2025-06-06 | 2025-07-20 | 45 | 18000000 | 16500000 | 100 | 85 | In Progress | Substructure
3.2 | Pier Cap & Bearings | 2025-07-21 | 2025-08-10 | 21 | 8500000 | 7200000 | 100 | 70 | In Progress | Substructure
4.1 | Precast Segment Casting Yard Setup | 2025-05-01 | 2025-05-15 | 15 | 4000000 | 4000000 | 100 | 100 | Completed | Superstructure
4.2 | Segment Casting | 2025-05-16 | 2025-08-30 | 107 | 22000000 | 19500000 | 100 | 75 | In Progress | Superstructure
4.3 | Segment Erection | 2025-09-01 | 2025-10-15 | 45 | 28000000 | 21000000 | 100 | 60 | In Progress | Superstructure
5.1 | Deck Slab & Girder | 2025-10-16 | 2025-11-15 | 31 | 15000000 | 8000000 | 100 | 40 | In Progress | Superstructure
5.2 | Barriers & Parapets | 2025-11-16 | 2025-12-05 | 20 | 6000000 | 1200000 | 100 | 15 | Not Started | Finishing
6.1 | Finishing Works & Painting | 2025-12-06 | 2025-12-20 | 15 | 4500000 | 0 | 100 | 0 | Not Started | Finishing
6.2 | Electrical & MEP Installation | 2025-12-21 | 2026-01-10 | 21 | 7000000 | 0 | 100 | 0 | Not Started | Finishing
7.1 | Testing & Commissioning | 2026-01-11 | 2026-01-25 | 15 | 3500000 | 0 | 100 | 0 | Not Started | Finishing

## Progress_Tracking
Week_Date | Activity_ID | Actual_%_Complete
2025-04-10 | 1.1 | 100
2025-04-20 | 1.2 | 100
2025-05-15 | 2.1 | 100
2025-06-05 | 2.2 | 95
2025-07-20 | 3.1 | 85
2025-08-10 | 3.2 | 70
2025-05-15 | 4.1 | 100
2025-08-30 | 4.2 | 75
2025-10-15 | 4.3 | 60
2025-11-15 | 5.1 | 40
2025-12-05 | 5.2 | 15
2025-12-20 | 6.1 | 0
2026-01-10 | 6.2 | 0
2026-01-25 | 7.1 | 0

## Costs
Month | Planned_Cum_Cost | Actual_Cum_Cost
2025-04-01 | 4000000 | 3880000
2025-05-01 | 19500000 | 18580000
2025-06-01 | 31000000 | 29500000
2025-07-01 | 49000000 | 46000000
2025-08-01 | 68500000 | 63200000
2025-09-01 | 90500000 | 82700000
2025-10-01 | 118500000 | 103700000
2025-11-01 | 133500000 | 111700000
2025-12-01 | 139000000 | 112900000
2026-01-01 | 142500000 | 112900000

## Materials
Material_Name | Planned_Qty | Actual_Consumed | Unit | Unit_Cost
Cement (OPC 53) | 12000 | 10500 | MT | 6500
TMT Steel (12mm) | 850 | 720 | MT | 72000
Ready Mix Concrete | 4500 | 3800 | Cum | 8500
Aggregates | 18000 | 16200 | Cum | 1200
Precast Segments | 240 | 165 | Nos | 125000